## ProjectSchedule
Smart Greenhouse Monitoring System based on Machine Learning
HDBTC |  | Project Start: | 2024-09-04
Dr. Pham Van Dai |  | Project End: | 2024-11-24
Week
TASK DISCRIPTION |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Initiation and Planning | Register the project | bar: Week 1
Define the project scope and objectives | bar: Week 1
Make initial contact with the supervisor | bar: Week 1
Draft the email for client | bar: Week 1
Send the email to the client | bar: Week 2
Conduct the initial client meeting | bar: Week 3
Develop the project plan | bar: Week 3 to Week 5
Create the Software Quality Assurance Plan | bar: Week 3 to Week 5
Requirements and Design | Gather requirements from stakeholders | bar: Week 6
Analyze and prioritize the requirements | bar: Week 6
Review and incorporate feedback on requirements | bar: Week 6
Research system architecture | bar: Week 7 to Week 8
Define the system components | bar: Week 8 to Week 9
Conduct a review of the system design | bar: Week 9
Development and Implementation | Develop the frontend | bar: Week 7 to Week 8
Develop the backend | bar: Week 8 to Week 9
Integrate machine learning functionality | bar: Week 7 to Week 11
Define test cases for the system | bar: Week 8
Test the system in iterations | bar: Week 8 to Week 11
Fix identified bugs and issues | bar: Week 8 to Week 11
Testing and Delivery | Prepare and deliver project presentations | bar: Week 12
Submit the project for peer review and supervisor feedback | bar: Week 12